## Sheet1
Time plan for Master Major Project
| September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February
Tasks | Wk36 | Wk37 | Wk38 | Wk39 | Wk40 | Wk41 | Wk42 | Wk43 | Wk44 | Wk45 | Wk46 | Wk47 | Wk48 | Wk49 | Wk50 | Wk51 | Wk52 | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk9
Make plan of approach | bar: September Wk36 to October Wk42
Make a floor plan | bar: September Wk39 to October Wk41
Set a Network and configure all devices | bar: October Wk41 to October Wk44
Literature Survey | bar: September Wk36 to December Wk51; January Wk2
Modelling and Simulation of Delta-robot | bar: October Wk44 to December Wk51
Identify and connect necessary sensors | bar: October Wk43 to November Wk46
Controller programming | bar: November Wk45 to December Wk51; January Wk2 to January Wk4
Simulate Control loop | bar: November Wk45 to December Wk51; January Wk2 to January Wk4
Test runs and debugging | bar: December Wk50 to December Wk51; January Wk2 to February Wk9
Make report | bar: October Wk42 to December Wk51; January Wk2 to February Wk6
Report submission and defense | bar: February Wk7
Extra: Fine-tuning | bar: January Wk2 to February Wk9
Legend
Holiday
If software is available sooner
Buffer